## Q-Stories
Angelo Danducci |  |  |  | Quad-Solver Stories
Jonah Groendal |  |  | Quadratic Formula:
Joshua Looney |  |  | X = (−b±√( b 2 −4ac )) / 2a
Jacob Schuurmans
Jake McClure
Task | Time(hours) | Risk | Actual Time | % Complete
As a user the quad solver will be a command line tool to solve quadratic equations (epic) | 8 | 4 | 4 | 50
Command line tool will allow the user to input three values – a,b,c as above | 1 | 3 | 1 | 100
Checks for accuracy and precision and warns the user if they are not high enough | 5 | 5 | 2 | 50
Returns single, double, or no root to the user through the terminal with single precision IEEE floating point | 2 | 3 | 1 | 50
Asks the user if they would like to solve additional problems or quit. | 1 | 2 | 0 | 0
TOTAL | 17 |  | 8

## Q-TPS
Angelo Danducci | TPS: Quad-Solver
Jonah Groendal | Quadratic Formula:
Joshua Looney | X = (−b±√( b 2 −4ac )) / 2a
Jacob Schuurmans
Jake McClure
Task | Time(hours) | Risk | Who? | Actual Time | % Complete | Reviewed? | Comments
Version Control | 3 | 2 | Jonah | 2 | 66 | Y | Basic Github set up for QS
Automation | 3 | 5 | Angelo | 1 | 30 | N | *Related to our framework.
Programming Standards | 2 | 2 | Jake | 1 | 60 | N | GNU C Code Standard. Need to update code to follow the standard
Language | 0.5 | 1 | All | 0.25 | 100 | Y | All agreed this would be done in C.
Reference examples of Quad Solver | 2 | 2 | Josh | 1 | 100 | Y | Gathered a few online references, looked at R functions, and have references to my previously built functions.
Set up Git repostory | 2 | 3 | Jonah | 1 | 100 | Y | Git repository is set up and everyone is invited via student email.
Learn about CUNIT | 3 | 3 | Angelo/Josh | 1 | 30 | N | Learning how to use CUNIT testing
Input line Safely | 2 | 2 | Jack | 0.25 | 20 | N | Learn how to bring in a C string safely
IEEE Floating Point | 2 | 2 | Jack | 2 | 50 | N | Learn about IEEE floating points
TOTAL | 19.5 |  |  | 9.5

## Z-Stories
Angelo Danducci | Date: 03/27/2017 |  |  | Zoetis Stories
Jonah Groendal | Introduction: This document is meant to be a medium between client and project programmers. This project is meant to extract, clean, and prepare date in online peptide databases for machine learning algortihms.
Joshua Looney
Jacob Schuurmans
Jack McClure
Task | Time(hours) | Risk | Actual Time | % Complete
User will have access to a single database which is an aggregate of public peptide databases that includes peptides up to length 50 | 5 | 4 | 2 | 30
User will be able to query the database for a given peptide and receive known properties | 5 | 4 | 0 | 0
User will have the ability to run an update tool which re-aggregates and adds new peptides / updates existing ones. | 5 | 4 | 0 | 0
User will be able to give a sample unknown peptide to a given program, and receive a prediction on the effects that the peptide may have (anti-fungal. etc) | 30 | 5 | 0 | 0
Release 1
User will be able to see predicted peptide activities from current databases. | 7 | 4
User will have access to new peptide databases, which will be updated and re-aggregated as previous ones are. | 4 | 3
Release 2
User will be able to query a free and open database complete with activities, papers and references, tools for helping download, various feature vector generation methods, and various machine learning methods with code. | 15 | 5
TOTAL | 45 |  | 2

## Z-TPS
Angelo Danducci | TPS: Zoetis
Jonah Groendal | Date: 03/27/2017
Joshua Looney
Jacob Schuurmans
Jack McClure
Task | Time(hours) | Risk | Who? | Actual Time | % Complete | Reviewed? | Comments
Version Control | 2 | 1 | Jonah | 2 | 100 | Y | Basic Github set up for Zoetis
Automation | 2 | 3 | Angelo | 1 | 80 | N | *Related to our framework.
Programming Standards | 2 | 2 | Jake | 1 | 100 | Y | Researched Python coding Standards, found a few different resources.
Language | 0.5 | 1 | All | 0.25 | 100 | Y | All agreed this would be done in Python.
Reference examples of databases | 2 | 2 | Josh | 1 | 100 | Y | Looked into R and Python functions for data cleaning and aggregation.
Set up Git repostory | 2 | 3 | Jonah | 1 | 100 | Y | Git repository is set up and everyone is invited via student email.
Split Databases evenly and look into donloading/cleaning them. | 5 | 4 | All/Divided | 6 | 95 | Y | Databases divided, each member responsible for reporting on their databases.
Report on databases | 2 | 2 | All/Divided | 0.5 | 15 | N | Meeting scheduled to review databases and best methods for cleaning.
Begin building Python code for data cleaning. | 4 | 3 | Josh/Angelo |  | 0 | N | Discuss best method for cleaning all databases, design program first, revise, then code.
TOTAL | 21.5 |  |  | 12.75

## Sheet1
Angelo Danducci | TPS: Zoetis
Jonah Groendal | Date: 03/13/2017
Joshua Looney
Jacob Schuurmans
Jack McClure
Task | Time(hours) | Risk | Who? | Actual Time | % Complete | Reviewed? | Comments
Split Databases evenly and look into downloading/cleaning them. | 10 | 4 | All/Divided | 4 | 40 | N | Databases divided, each member responsible for reporting on their databases.
Report on databases | 2 | 2 | All/Divided | 0 | 0 | N | Meeting scheduled to review databases and best methods for cleaning.
TOTAL | 12 |  |  | 4